## Proposals
Tracker ID | Proposal name | Category | Website link | Due date | Source | Matched keywords | Status | Owner | Date found | Notes
509c1233eb68c995 | Capital Markets Authority Tender Notice for Supply, Implementation, Training and Maintenance of a Virtual Assets Blockchain Analytics System | Analytics | https://gaa.go.ke/node/4279 | 2026-07-21 | myGov Kenya | analytics, training | Review required | Project team | 2026-08-08

## Workplan
Task | Owner | Start date | Due date | Status | Dependencies | Notes
Provide and prioritise source website links | Olivia | 2026-08-08 | 2026-08-10 | Not started |  | Add approved ministry and donor portals to the source intake.
Confirm keywords and exclusion terms | Olivia | 2026-08-08 | 2026-08-10 | Not started | Source list | Confirm analytics, data science, training, and exclusion terms.
Add approved sources and complete a test scrape | Technical owner | 2026-08-11 | 2026-08-13 | Not started | Olivia source links | Activate and validate each source before recurring monitoring.
Configure Tuesday/Thursday myGov alert recipient | Olivia / Technical owner | 2026-08-11 | 2026-08-15 | Not started | SMTP access | Set alert recipient and SMTP details in .env.
Review new opportunities and assign a proposal owner | Project team | 2026-08-13 | 2026-08-20 | Ongoing | Proposal tracker | Update proposal status, owner, and notes after each scan.
Define content-folder approval and posting workflow | Olivia / Content owner | 2026-08-15 | 2026-08-22 | Not started | Content folder | Confirm approval steps before connecting posting automation.
Review performance and refine keywords | Project team | 2026-08-22 | 2026-08-29 | Not started | Two weeks of results | Remove irrelevant results and add useful new terms.

## Website Register
Source name | Website URL | Type | Priority | Check frequency | Active | Notes

## Keywords
Keyword | Category | Include / Exclude | Notes
analytics | Analytics | Include
data science | Data science | Include
training | Training | Include

## Content Calendar
Content item | Platform | Owner | Approval status | Posting date | Published | Notes

## Workflow Queue
Tracker ID | Proposal | Next action | Owner | Review due date | Status | Link
509c1233eb68c995 | Capital Markets Authority Tender Notice for Supply, Implementation, Training and Maintenance of a Virtual Assets Blockchain Analytics System | Review proposal and assign a bid decision | Project team | 2026-08-08 | Review required | https://gaa.go.ke/node/4279

## Workflows
Workflow | Trigger | Automated action | Owner | Output / escalation
Proposal discovery | Scheduled monitoring finds a keyword match | Create or update a persistent review task | Project team | Workflow Queue; review due date is three days before tender close.
myGov alert | Tuesday/Thursday scheduler finds new matches | Send one email per new opportunity | Project team | Scheduler waits for SMTP configuration and prevents repeat alerts.
Proposal review | Workflow Queue contains Review required | Assess relevance and set bid decision | Proposal owner | Update the workflow state using the command below.
Content publishing | Content receives approval | Queue item for posting automation | Content owner | To be connected when the content folder/platform is provided.